## Tech_Backlog_MS
Component | Work package | Type (FE/BE/AI/DB/Infra/Cross) | Description | Complexity (S/M/L) | Estimated days
cross_backend_architecture | API contract definitions (OpenAPI/schema) | Cross | Define and document API contracts and shared schemas between microservices. | L | 7
cross_backend_architecture | Domain model consolidation | Cross | Consolidate domain entities across services (RFQ, stage, workflow, reminder, IAM) and align schemas. | L | 7
cross_backend_architecture | Microservices architecture design | Cross | Define microservices boundaries (rfq_manager_ms, rfq_reminder_ms, iam_ms, rfq_chatbot_ms), communication patterns, and contracts. | L | 7
cross_devops | Deployment automation (CI/CD) | Infra | Implement CI/CD pipelines for build, test, and deployment to AKS. | L | 7
cross_devops | Environment setup (Dev/Int) | Infra | Create and configure Dev and Integration environments for the solution. | M | 4
cross_devops | Solution packaging toolchain | Infra | Define and implement packaging (Docker images, Helm charts) for all microservices and frontend. | L | 7
cross_frontend_design | UX flows & information architecture | Cross | Design main UX flows per page (overview, RFQ management, RFQ view, admin) and navigation structure. | M | 4
cross_frontend_design | Wireframes / UI guidelines | Cross | Produce wireframes and guidelines for key pages and components. | M | 4
cross_infrastructure_design | Cloud architecture & resources design | Infra | Design Azure resources: AKS, OpenAI service, Azure SQL, Key Vault, ACR, Storage Account, networking. | L | 7
cross_infrastructure_design | Security & network design | Infra | Define network isolation, ingress (App Gateway), SSL, certificates, and access policies. | L | 7
cross_opex | Cost monitoring & optimization baseline | Infra | Define tagging, monitoring, and first optimisation recommendations for cloud cost. | S | 2
cross_opex | OPEX cost model design | Cross | Estimate recurring costs for SSL certificates, domain, Azure resources (OpenAI, SQL, Key Vault, ACR, Storage). | M | 4
cross_tests_deployment | Deploy Dev solution | Infra | Deploy full solution stack to Dev environment. | M | 4
cross_tests_deployment | Functional tests with client (UAT support) | QA/Cross | Prepare scenarios and support client for UAT sessions. | L | 7
cross_tests_deployment | Integration tests | QA/Cross | Implement and execute integration tests across microservices and frontend. | L | 7
frontend_app | Admin UI – IAM (users, roles, permissions, groups) | FE | Implement IAM administration screens on the frontend. | L | 7
frontend_app | Admin UI – stages & workflows | FE | Implement admin pages to manage stages and workflows. | L | 7
frontend_app | Copilot panel UI in RFQ view | FE | Integrate chatbot/copilot panel for the Estimation stage into RFQ view. | M | 4
frontend_app | Frontend shell & IAM integration | FE | Implement app shell (layout, routing, IAM-based menu visibility, authentication flow). | L | 7
frontend_app | Frontend tests (unit & e2e smoke) | QA/FE | Write critical-path tests for navigation, RFQ lifecycle, and copilot panel. | M | 4
frontend_app | Overview page UI | FE | Implement overview page with shortcuts to RFQs and dashboards. | S | 2
frontend_app | RFQ view & workflow UI | FE | Implement RFQ details page with workflow visualization, current step, and stage edit actions based on IAM. | L | 7
frontend_app | RFQs management dashboard UI | FE | Implement dashboard page with RFQ list, filters, and basic KPIs. | L | 7
iam_ms | IAM admin tests & security checks | QA/Cross | Write tests for IAM flows and perform a basic security review of permissions. | M | 4
iam_ms | IAM data model (user, role, group, permission) | BE/DB | Design IAM entities and relations (users linked to departments/teams, groups, roles, permissions per action). | L | 7
iam_ms | Permission evaluation component | BE | Implement permission checking logic and policy evaluation (backend actions & front-end routes). | M | 4
iam_ms | Token / auth integration | BE/Infra | Integrate authentication (JWT or similar) and expose user claims/permissions to other microservices. | M | 4
iam_ms | User, role, group, permission CRUD APIs | BE | Implement CRUD endpoints for IAM entities. | M | 4
rfq_chatbot_ms | Chat API endpoints | BE/AI | Implement endpoints to send/receive chat messages, orchestrating LLM calls and context building. | L | 7
rfq_chatbot_ms | Chatbot entity & CRUD | BE/DB | Model chatbot configuration entity (name, scope, prompts) and implement CRUD. | M | 4
rfq_chatbot_ms | Chatbot service skeleton | BE/AI | Create chatbot microservice skeleton with connection to LLM provider. | M | 4
rfq_chatbot_ms | Chatbot tests (unit & integration) | QA/AI | Test typical copilot/Estimation flows including RFQ context retrieval. | M | 4
rfq_chatbot_ms | Conversation & history model | BE/DB | Model conversation sessions and message history linked to RFQ and user. | M | 4
rfq_chatbot_ms | Integration with rfq_manager_ms | BE/AI | Retrieve RFQ data and documents from rfq_manager_ms to build copilot context for Estimation stage. | L | 7
rfq_chatbot_ms | Logging & telemetry for chatbot | BE | Log conversations, errors, and latency for observability and tuning. | M | 4
rfq_manager_ms | Backend skeleton & common modules | BE/Cross | Create rfq_manager_ms project skeleton (framework, logging, error handling, config management). | M | 4
rfq_manager_ms | Dashboard APIs (RFQ list & KPIs) | BE/Data | Implement APIs to provide RFQ list with filters and basic aggregated KPIs used by dashboards. | L | 7
rfq_manager_ms | IAM integration (authorization checks) | BE | Integrate IAM permissions into rfq_manager_ms endpoints (who can edit RFQ, stage, workflows, reminders). | M | 4
rfq_manager_ms | RFQ entity & CRUD API | BE/DB | Model RFQ entity and implement create, read, update, delete endpoints including basic validation. | M | 4
rfq_manager_ms | RFQ stage instance model | BE/DB | Design RFQ stage instance entity linked to RFQ and workflow_stage, including flexible attributes and required fields. | M | 4
rfq_manager_ms | Reminder configuration model | BE/DB | Model reminder configuration (internal/client, timing, stage blueprint) and expose CRUD APIs. | M | 4
rfq_manager_ms | Unit & integration tests for rfq_manager_ms | QA/BE | Write tests covering core RFQ, stage, workflow, dashboard and reminder configuration flows. | M | 4
rfq_manager_ms | Update stage action API | BE | Implement endpoint to update RFQ stage data, enforce mandatory fields and stage transitions. | L | 7
rfq_manager_ms | Workflow model & CRUD | BE/DB | Model workflow entity with many-to-many relationship to workflow_stage and implement CRUD. | M | 4
rfq_manager_ms | Workflow_stage model & CRUD | BE/DB | Model workflow_stage as stage unit and implement CRUD for stage definitions. | M | 4
rfq_reminder_ms | Client reminder rules engine | BE | Implement logic to evaluate client follow-up reminders after proposal submission. | S | 2
rfq_reminder_ms | Email sending integration | BE/Infra | Integrate with email provider (SMTP/API), handle templates and error handling. | M | 4
rfq_reminder_ms | Integration with rfq_manager_ms | BE | Implement client to query rfq_manager_ms for RFQs and stages requiring reminders based on configuration. | M | 4
rfq_reminder_ms | Internal reminder rules engine | BE | Implement logic to evaluate internal reminders (team notifications before deadlines and SLA breaches). | M | 4
rfq_reminder_ms | Reminder logging & retry mechanism | BE/DB | Persist sent reminders, errors, and implement basic retry for failed notifications. | M | 4
rfq_reminder_ms | Service skeleton & scheduling framework | BE/Infra | Create rfq_reminder_ms service skeleton and integrate cron/scheduler framework. | M | 4
rfq_reminder_ms | Tests for reminder flows | QA/BE | Tests for internal and client reminder scenarios end-to-end. | M | 4
259
Man Charge | 259
TJM USD | 250
Total USD | 64750
OPEX Monthly Licence | 1500

## Component_Summary
Component | Total_days
rfq_manager_ms | 46
frontend_app | 45
rfq_chatbot_ms | 34
rfq_reminder_ms | 26
iam_ms | 23
cross_backend_architecture | 21
cross_devops | 18
cross_tests_deployment | 18
cross_infrastructure_design | 14
cross_frontend_design | 8
cross_opex | 6
TOTAL | 259
TJM USD | 250
Total USD | 64750
OPEX Monthly Licence USD | 1500